Climate Action Plan

Potton Primary School

1 year plan Autumn 2025 – 2025

Carbon baseline: 322.32 tCO2e per year      Calculation: 13th November 2025

caaname@letsgozero.org

| GET STARTED |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTION | TIMEFRAME | STAKEHOLDERS | NOTES | TRACKER |
| Sign up to the Let’s Go Zero campaign | Start: September 2025 Review: October 2025 | Senior Leadership Team (SLT), Eco-committee, School Business Manager | Complete the online registration at letsgozero.org/join. Announce the commitment to staff, students, and parents via newsletter and assembly. Display the Let’s Go Zero logo on the school website and noticeboards. |  |
| Calculate your school’s carbon footprint using Count Your Carbon | Start: September 2025 Review: November 2025 | School Business Manager, Site Manager, Eco-committee | Gather data on energy, water, waste, food, and transport. Use the free Count Your Carbon tool to calculate the baseline. Share results with the school community and use findings to inform further actions. |  |
| Sign up to the Sustainability Support for Education | Start: September 2025 Review: October 2025 | SLT, Eco-committee, Teaching Staff | Register for the DfE-funded support platform. Explore and filter resources relevant to primary education and current priorities. Assign a staff member to coordinate use of resources and track progress. |  |

1. Decarbonisation and Energy Efficiency
Calculating and taking actions to reduce carbon emissions and becoming more energy efficient

| ENERGY – BEHAVIOUR CHANGE |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTION | TIMEFRAME | STAKEHOLDERS | NOTES | TRACKER |
| Take part in a switch off campaign (e.g. Switch-Off Fortnight) | Start: Autumn 2025 Review: End of campaign | Eco-committee, Site Manager, All staff & pupils | Set up a competition between classes for most energy saved. Share results in assemblies. |  |
| Create awareness of energy use in school through posters and assemblies | Start: Autumn 2025 Review: Termly | Eco-committee, Teachers | Design posters with students. Hold a launch assembly. |  |

| ENERGY – BUILDINGS & INFRASTRUCTURE |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTION | TIMEFRAME | STAKEHOLDERS | NOTES | TRACKER |
| Install a smart meter | Start: Autumn 2025 Review: Spring 2026 | Site Manager, Business Manager | Contact supplier for installation. Use data for lessons. |  |
| Conduct an energy audit of school buildings | Start: Autumn 2025 Review: Annually | Site Manager, Local Authority | Identify areas for insulation, draft-proofing, LED upgrades. |  |

| PROCUREMENT |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTION | TIMEFRAME | STAKEHOLDERS | NOTES | TRACKER |
| Develop a Sustainable Procurement policy | Start: Autumn 2025 Review: Annually | Business Manager, SLT | Prioritise suppliers with environmental credentials. |  |

| FOOD |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTION | TIMEFRAME | STAKEHOLDERS | NOTES | TRACKER |
| Offer a vegan/vegetarian option every day | Start: Autumn 2025 Review: Termly | Catering Manager, Pupils | Survey students for preferences. Promote new options. |  |
| Reduce food waste through poster campaigns and assemblies | Start: Autumn 2025 Review: Termly | Eco-committee, Catering Manager | Weigh food waste weekly. Share results. |  |

| TRANSPORT |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTION | TIMEFRAME | STAKEHOLDERS | NOTES | TRACKER |
| Conduct a staff and student travel survey | Start: Autumn 2025 Review: Annually | Eco-committee, Admin | Use results to promote walking, cycling, car share. |  |

| WASTE |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTION | TIMEFRAME | STAKEHOLDERS | NOTES | TRACKER |
| Start/expand recycling to other materials | Start: Autumn 2025 Review: Termly | Site Manager, Eco-committee | Add bins for batteries, pens, textiles. |  |
| Start new refuse contract – focus on food waste & recycling | Start: Autumn 2025 Review: Annually | Business Manager | Compare costs and environmental impact. |  |

2. Climate adaptation and resilience
Taking actions to reduce the risk of flooding and overheating and to future-proof scarce resources for potential shortages

| ADAPTATION AND RESILIENCE |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTION | TIMEFRAME | STAKEHOLDERS | NOTES | TRACKER |
| Write a heatwave policy | Start: Autumn 2025 Review: Annually | SLT, Governors | Consult staff, parents. Share policy widely. |  |
| Clear drains around the school site | Start: Autumn 2025 Review: Termly | Site Manager | Schedule regular checks, especially before heavy rain. |  |

| WATER |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTION | TIMEFRAME | STAKEHOLDERS | NOTES | TRACKER |
| Install systems to reduce water wastage | Start: Autumn 2025 Review: Annually | Site Manager | Fit push taps, check for leaks, monitor bills. |  |
| Install water butts at drainage points | Start: Autumn 2025 Review: Spring 2026 | Site Manager, Eco-committee | Use water for gardens, Forest School. |  |

3. Biodiversity and Green Infrastructure
Creating habitats and adopting practices that will enhance species diversity on the school estate and beyond

| NATURE |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTION | TIMEFRAME | STAKEHOLDERS | NOTES | TRACKER |
| Enroll with The Nature Park (NENP) | Start: Autumn 2025 Review: Annually | Eco-committee, Teachers | Use resources for lessons and projects. |  |
| Explore tree planting in Forest School/Roots field | Start: Autumn 2025 Review: Spring 2026 | Eco-committee, Site Manager | Apply for free trees from Woodland Trust. |  |
| Explore ‘rewilding’ parts of Roots field | Start: Autumn 2025 Review: Annually | Eco-committee, Teachers | Leave areas unmown, plant wildflowers. |  |

4. Climate Education, Green Skills and Green Careers
Ensuring the education you provide gives knowledge-rich and comprehensive teaching about climate change, and that your teaching staff feel supported to offer this

| CULTURE |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTION | TIMEFRAME | STAKEHOLDERS | NOTES | TRACKER |
| Set up an eco-committee for pupils | Start: Autumn 2025 Review: Annually | Teachers, Pupils | Rotate membership, link to School Council. |  |

| CURRICULUM |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTION | TIMEFRAME | STAKEHOLDERS | NOTES | TRACKER |
| Complete a curriculum audit & incorporate sustainability | Start: Autumn 2025 Review: Annually | Teachers, SLT | Use Teach the Future and MoEE resources. |  |

| GREEN SKILLS AND CAREERS |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTION | TIMEFRAME | STAKEHOLDERS | NOTES | TRACKER |
| Access the Climate Ambassadors scheme | Start: Autumn 2025 Review: Annually | Teachers, Pupils | Invite ambassadors for assemblies/workshops. |  |
| Invite visitors from environmental charities | Start: Autumn 2025 Review: Annually | Teachers, Pupils | Link to curriculum topics, careers week. |  |